## Slide 1
Recruit mentors & mentees via survey
March ‘21
April ‘21
May ‘21
Select & match mentors & mentees, schedule training for mentors
Conduct mentor training & mentor/mentee work through orientation materials
June ‘21
Sept ‘21
Dec ‘21
NE BIAC Mentor Program Timeline
March ‘22
Meet after first AC meeting & continue to work through orientation materials
Mentor/Mentee meet before & after AC meeting
Mentor/Mentee meet before & after AC meeting & Mentee Complete 6 mo. survey
Mentor/Mentee meet before & after AC meeting & Mentee Complete final survey
NE BIAC Mentor Program: Staff Timeline